## commission file number
(Commission File Number)
Delaware | 46-0408024
(State or other jurisdiction of incorporation) | (IRS Employer Identification No.)

## commission file number-1
Exhibit No. | Exhibit Description
99.1 | Unidym, Inc. News Release released dated May 13, 2009.

## signatures
SIGNATURES
ARROWHEAD RESEARCH CORPORATION
By: | /s/ Paul C. McDonnel
Paul C. McDonnel
Chief Financial Officer

## in witness whereof
IN WITNESS WHEREOF
Signed for and on behalf of Unidym, Inc. | Signed for and on behalf of LG Display Co., Ltd.
Name : Designation : | Name : Designation:

## jda timeline and milestone
JDA timeline and milestone
Unidym
Year |  |  | 2009-2010
Month |  |  | 1 | 2 | 3 |  | 4 | 5 | 6 | 7 |  | 8 | 9 | 10 | 11 | 12
Deliverable |  | Rs (Ohm/sq) Tr (CNT Only) at 550nm | 200 ohm/sq 85% |  |  |  |  | 200 ohm/sq 90% |  |  |  |  | 100 ohm/sq 92%
Key Technology development (Unidym) |  |  | Feasibility |  |  |  |  | Improvement (I) |  |  |  |  | Improvement (II)
|  |  | CNT raw material Development - Synthesis condition optimization |  |  |  |  | CNT raw material Development - Catalyst optimization |  |  |  |  | CNT raw material performance with large scale production
CNT Raw Material |  |  | Purification/solubilization (1) |  |  |  |  | Purification/solubilization (2) |  |  |  |  | Quality control (QC) for CNT performance
|  |  | Low light scattering CNT film (Haze below 0.2%) |  |  |  |  | Low light scattering CNT film (Haze below 0.1%) |  |  |  |  | Chemically stable Rs (DRs/Rs <10% with LGD stripper)
Dispersion |  |  | Dispersion optimization (No slit exiting block etc) |  |  |  |  | Dispersion cleaning (particle) - Filtration of dispersion |  |  |  |  | Doping (Environmental stability)
| Development of single path coating process dispersion (1) |  |  |  |  | Development of single path coating process dispersion (2) |  |  |  |  | Dispersion stability test for single path coating dispersion and film
|  |  | CNT coating process development (Dual path) : Washing/Drying, surface cleaning(particle) |  |  |  |  | Coating on large area glass CNT and topcoat equipment development |  |  |  |  | CNT coating process integration (W/LGD) New process development: Mask-less patterning
|  |  | Development of single path coating process (1) |  |  |  |  | Development of single path coating process(2) |  |  |  |  | Equipment modification for single path coating
Coating process & Device integration |  |  | Rs and Tr Uniformity (<20%), Uniformity = (Max- Min)/(Max+Min)*100 at 370 * 470 mm |  |  |  |  | Rs and Tr Uniformity (< 15%) |  |  |  |  | Rs and Tr Uniformity (< 10%)
|  |  | Surface activation for TFT-side coating |  |  |  |  | Metal/CNT contact resistance study |  |  |  |  | Metal/CNT contact resistance improvement
|  |  | Adhesion improvement (1) TAB rework available - Dual path coating |  |  |  |  | Adhesion improvement (1) TAP rework available- Single path coating |  |  |  |  | Adhesion improvement (2) TAP rework available-Single path coating
|  |  | Roughness reduction (RMS< 10nm) |  |  |  |  | Roughness reduction (RMS < 5nm) |  |  |  |  | Roughness reduction (RMS < 2 nm)

## lgdisplay
LG-Display
Year |  | 2009-2010
Month |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Deliverable | Rs(Ohm/sq) Tr (CNT only) at 550 nm | 200 ohm/sq 85% |  |  |  | 200 ohm/sq 90% |  |  |  | 100 ohm/sq 92%
Key Technology development (LGD) |  | Feasibility |  |  |  | Unit process set-up |  |  |  | Proto-type (I)
|  | Adhesion test _3M tape |  |  |  | Adhesion test_3M tape |  |  |  | Confirmation Spec-in CNT material
Material evaluation |  | Chemical stability |  |  |  | C/R test (CF pol btw TFT pol) |  |  |  | Chemical stability For new dispersion CNT
|  | Thermal stability (DRs/Rs<10%, at 230°C(1000sec) in air) |  |  |  | Improved CNT materials evaluation |  |  |  | Thermal stability for new dispersion CNT (DRs/Rs <5%, at 230 °C (1000 sec) in air)
Coating process |  | CNT coat on glass (LGD Slit coater) (Rs-Tr uniformity < 20%) |  |  |  | CNT coat on glass (Rs-Tr uniformity below 10%) Comparison dual and single path dispersion |  |  |  | CNT coat on glass for single path coating (Rs-Tr uniformity below 10%)
|  | In-house (LGD) Slit nozzle design and coating trial |  |  |  | Process integration 1 (Coating-washing- drying) |  |  |  | Process integration 2 (Coating- washing-drying)
|  | IPS electrode unit process test on CNT |  |  |  | Unit process set-up of CNT electrode for TFT backplane |  |  |  | Confirmation Spec-in CNT material
|  | Line resistance |  |  |  | Tab rework test (adhesion) |  |  |  | Target spec decision (IPS/TN LCD)
Device integration |  | CNT dry etch process set up Patterning of CNT film (IPS pattern) |  |  |  | Contact resistance test btw S/D and CNT electrode coated by LGD |  |  |  | LC process setup with CNT film 12 (PI, Rubbing, H/P etc)
|  | Rs test & Light scattering test |  |  |  | LC process feasibility (PI-CNT interaction etc) |  |  |  | IPS mode LCD proto-type 1 (17inch) With final dispersion